CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Ho Chi Minh, October 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 11/09/2026 | A | Project team | Create the initial Project Management Plan based on the Week 1 business baseline and the official SEP490 15-week roadmap. |
| 21/10/2026 | M | Trương Hoàng Quí | Aligned the plan with the implemented system: removed probation, Internal HR submission and duplicate marking; added consent, source disputes, Client fees and deposits, replacement slots, administration, supporting features and the planned Service Agreement to the WBS; updated responsibilities to actual ownership, tools, deliverables; removed duplicated table rows. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

HR Connect is a web platform that centralizes the recruitment workflow among the agency, client companies, candidates and Affiliate/OPR users. The product covers company and job management, candidate and submission management, AI-assisted CV-JD matching, the recruitment pipeline, Client service fees, warranty and affiliate commission tracking, and system administration. The following estimate uses ideal man-days and will be refined after the SRS and design baselines.

Table 2. Work Breakdown Structure and Effort Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Company and Job Management |  | 48 |
| 1.1 | Company profile and verification | Medium | 7 |
| 1.2 | Create and maintain Job/JD | Medium | 7 |
| 1.3 | Service type and requirements configuration | Medium | 6 |
| 1.4 | Job review, approval and publication | Complex | 10 |
| 1.5 | Public job search and status visibility | Medium | 8 |
| 1.6 | Service Agreement negotiation and OTP signing (planned) | Complex | 10 |
| 2 | Candidate, CV and Submission Management |  | 63 |
| 2.1 | Candidate master profile and identifiers | Complex | 10 |
| 2.2 | CV upload, storage and version linkage | Medium | 8 |
| 2.3 | Submission by Candidate or Affiliate | Complex | 10 |
| 2.4 | Email and phone normalization | Medium | 7 |
| 2.5 | Duplicate identification and blocking (BLOCKED_DUPLICATE) | Complex | 10 |
| 2.6 | Submission source, attribution and audit history | Complex | 10 |
| 2.7 | Candidate consent and source disputes | Complex | 8 |
| 3 | AI Matching and Screening Support |  | 45 |
| 3.1 | CV and JD parsing/preparation | Complex | 10 |
| 3.2 | Must-have and Should-have comparison | Complex | 10 |
| 3.3 | Match Score and Match Tier | Complex | 10 |
| 3.4 | Candidate Highlight and reviewer display | Medium | 8 |
| 3.5 | AI result storage, retry and traceability | Medium | 7 |
| 4 | Recruitment Workflow and Placement |  | 62 |
| 4.1 | Application and screening status | Medium | 8 |
| 4.2 | Interview scheduling and notification | Complex | 10 |
| 4.3 | Interview result and feedback | Medium | 8 |
| 4.4 | Offer and candidate response | Complex | 10 |
| 4.5 | Start work and placement confirmation | Complex | 10 |
| 4.6 | Warranty, resignation and replacement slot | Complex | 10 |
| 4.7 | Status history and exception outcomes | Medium | 6 |
| 5 | Affiliate, Fees, Commission and Reporting |  | 58 |
| 5.1 | OPR profile and activation | Medium | 7 |
| 5.2 | Affiliate job and submission visibility | Medium | 8 |
| 5.3 | Commission eligibility and rule application | Complex | 10 |
| 5.4 | Commission approval, holding, adjustment and payable status | Complex | 8 |
| 5.5 | Payout ledger and history | Medium | 7 |
| 5.6 | Affiliate quality and pipeline reporting | Complex | 10 |
| 5.7 | Client posting fees, service fees and Sourcing deposit | Complex | 8 |
| 6 | Platform Foundation |  | 34 |
| 6.1 | Authentication and role-based authorization | Complex | 8 |
| 6.2 | Real-time notifications and audit logging | Medium | 6 |
| 6.3 | Deployment configuration and monitoring | Medium | 6 |
| 6.4 | Administration: roles, approvals and business settings | Medium | 6 |
| 6.5 | CV Builder, AI job suggestions and contact form | Medium | 8 |
| Total Estimated Effort (man-days) |  |  | 310 |

### 1.2 Project Objectives

Overall objective: deliver an operational HR Connect web platform within the 15-week SEP490 Capstone period. The platform will support the three recruitment service types Headhunt COD, CV Sourcing and CV Application, maintain traceable candidate submissions, provide AI-assisted matching for human review, track recruitment milestones, and manage affiliate rights and commission records. Final behavior must remain consistent across the approved Blueprint, SRS, design, source code, tests and demonstration.

Table 3. Project Quality and Testing Targets

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% baseline documents and pull requests reviewed | Actual recorded weekly | 100% recorded | Resolve review comments before baseline. |
| 2 | Unit Test | At least 70% of agreed backend business logic | Actual from CI | By stage | Focus on validation, states, attribution and commission logic. |
| 3 | Integration Test | 100% critical API, database and AI integration scenarios | Actual from tracker | By stage | Include authorization, failure and retry scenarios. |
| 4 | System Test | 100% planned critical main-flow and exception scenarios | Actual from test report | By stage | No open blocker or critical defect before release. . |
| 5 | Acceptance Test | 100% of the five approved main flows demonstrated | Actual from UAT | By stage | Evidence must match SRS, design and deployed behavior. |

- All five approved main flows have end-to-end acceptance scenarios and traceability to design, code and test evidence.
- 100% of critical and high-severity defects are closed before the final submission; no unresolved blocker remains.
- At least 70% unit-test coverage for backend business-logic components, measured on the agreed testable scope.
- Authorization, duplicate marking, status transition and commission rules are covered by integration or system tests.
- AI results are treated as decision support; shortlist, reject, interview and offer decisions require an authorized human actor.

- Milestone timeliness: at least 90% of committed weekly deliverables completed by the planned checkpoint; all mandatory Review and Council packages submitted by the school deadline.

- Allocated effort: 375 man-days, based on 5 members x 15 weeks x 5 working days. Baseline distribution: Project Management 40; Requirements 45; Design 55; Implementation 170; Testing and Quality Assurance 65 man-days.

- Cost baseline: the project uses student effort and free or education-tier tools. Any paid cloud, AI API or external service must be approved by the team and recorded as a project cost before use.

### 1.3 Project Risks

The team reviews the following risks every week. Probability and impact use Low, Medium and High. A risk becomes an issue when it occurs and must then have an owner, action and target date in the weekly tracker.

Table 4. Project Risk Management Plan

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Unconfirmed business rules for the three service types, attribution, commission or payout cause rework. | High | High | Maintain a Decision Log; mark unresolved rules as TBD; obtain supervisor confirmation before implementation. |
| 2 | Scope exceeds the 15-week capacity of five members. | High | High | Prioritize the five approved main flows; apply change control; move optional analytics, integrations and advanced AI to future scope. |
| 3 | Duplicate and master-candidate behavior is implemented inconsistently across UI, API and database. | High | Medium | Define one canonical rule set in SRS; add API validation and integration tests; review with traceability. |
| 4 | AI output is unreliable, unavailable or too costly. | High | Medium | Keep human review mandatory; implement timeout/retry and a manual fallback; monitor usage and store result metadata. |
| 5 | Personal candidate data is exposed to unauthorized users. | High | Medium | Apply least privilege, masking where required, audit logs, secure file access and authorization tests. |
| 6 | Frontend-backend contracts diverge during parallel development. | Medium | High | Baseline OpenAPI contracts, use mock responses, version changes and run integration checks continuously. |
| 7 | Late defect discovery affects Review or Council readiness. | High | Medium | Test each increment; maintain CI; reserve W12 for system testing and defect closure. |
| 8 | Team contribution or evidence is incomplete. | Medium | Medium | Update weekly task and evidence tracker; link commits, documents, tests and demonstrations to each task. |
| 9 | Deployment environment differs from development. | High | Medium | Use versioned environment configuration, deployment checklist, seed data and rehearsal deployment before W12. |
| 10 | Documents, source code, tests and demo become inconsistent. | High | Medium | Perform traceability review at each baseline and a final consistency audit in W14. |

## 2. Management Approach

The project uses an incremental approach organized by the five approved main flows. The team maintains one prioritized backlog and implements a vertical slice in each increment: clarified requirement, design update, implementation, unit and integration tests, demonstration and evidence. Weekly planning and tracking follow the official SEP490 schedule. Scope changes require an impact assessment covering requirements, schedule, effort, design, tests and demo.

### 2.1 Project Process

Process model: Incremental development with weekly control. W1-W3 establish project understanding, planning and requirements. W4 is the first baseline review. W5-W7 establish architecture, data design and test preparation. W8-W11 implement and demonstrate main-flow increments. W12 performs system testing and final readiness. W13 is the Faculty Council checkpoint. W14 closes feedback and performs cross-document consistency checks. W15 completes final submission and defense preparation. Each increment follows: Plan -> Analyze -> Design -> Implement -> Test -> Review -> Demonstrate -> Record Evidence.

### 2.2 Quality Management

Quality is built into each increment. The team applies the following controls:

- Defect prevention: maintain a Decision Log, definition of done, coding conventions, API contracts, database migration rules, environment templates and security requirements before implementation.

- Reviewing: review requirements, designs and test cases against the approved Blueprint; require pull-request review for changes to protected branches; record feedback and closure evidence.

- Unit testing: developers test business logic and error paths. Backend business-logic coverage target is at least 70% for the agreed measurable scope.

- Integration testing: verify API-database behavior, role permissions, external AI communication, notifications and the hand-off between main flows.

- System testing: execute end-to-end happy paths and critical exceptions for all five main flows in a production-like environment. Re-test corrected defects.

Acceptance testing: demonstrate the deployed product using controlled accounts and data. A feature is accepted only when requirement, design, code, test and demo evidence are consistent.

### 2.3 Training Plan

### Table 5. Project Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| HR Connect Blueprint, service types and five main flows | All members | W1-W2, 4 hours | Explain assigned main flow and pass team review. |
| Git workflow, pull requests and CI | All members | W1-W2, 3 hours | Create a reviewed pull request and resolve a conflict. |
| ASP.NET Core, Entity Framework Core and API security | Backend contributors | W2-W5, 8 hours | Complete the technical spike and reviewed API task. |
| Frontend framework, API integration and role-based UI | Frontend contributors | W2-W5, 8 hours | Complete a reviewed UI-to-API vertical slice. |
| AI matching integration, prompt/output schema and fallback | AI/integration contributors | W5-W7, 6 hours | Demonstrate schema validation, timeout and fallback behavior. |
| Testing, traceability and evidence management | All members | W3-W7, 4 hours | Write and execute approved test cases with linked evidence. |
| Deployment, configuration and monitoring | Assigned deployment members | W7-W11, 4 hours | Complete a rehearsal deployment from documented steps. |

## 3. Project Deliverables

The master schedule below follows the school sample and the current 15-week SEP490 execution roadmap. Dates are expressed by academic week because the official calendar dates may be updated by the course. Each deliverable must include evidence and a version recorded in the team tracker.

Table 6. Project Deliverables and Schedule

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 - Project Introduction and Core Blueprint baseline | W1 | Problem, objectives, actors, scope, capabilities and main flows. |
| 2 | Report 2 - Project Management Plan v0.9 | W2 | Scope estimate, objectives, risks, process, schedule and responsibilities. |
| 3 | SRS baseline and Project Plan update | W3-W4 | Business rules, use cases, exceptions, permissions, data dictionary and acceptance criteria. |
| 4 | Architecture and Design baseline | W5-W8 | Architecture, database, APIs, UI flows, state models, deployment and security design. |
| 5 | Incremental software packages and test evidence | W8-W11 | Implemented main flows, CI results, test cases, demos and traceability. |
| 6 | System Test Report and release candidate | W12 | End-to-end results, defect status, installation and release evidence. |
| 7 | Report 3 - Project Tracking (WBS, issues, defects, Q&A) | W1-W15 | Updated weekly; the WBS status follows the delivered increments. |
| 8 | Final report, slides and demonstration package | W13-W15 | Faculty Council checkpoint, feedback closure and final defense. |

## 4. Responsibility Assignments

Table 7. Responsibility Assignment Matrix

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | TriCHSE184047 | SonKNSE184040 | QuiTHSE184355 | MiLTTSE184379 | SangNVSE183276 |
| --- | --- | --- | --- | --- | --- |
| Project planning, tracking and reporting | R | S | D | S | S |
| Requirements and cross-document consistency | R | R | D | R | R |
| MF-01 Create, approve and publish Job | D | I | R | S | S |
| MF-02 Candidate submission, consent, duplicate blocking and source | D | I | R | I | S |
| MF-03 AI Matching and screening support | S | S | D | I | S |
| MF-04 Candidate recruitment workflow | I | D | R | I | S |
| MF-05 Post-hire, commission and payout | I | S | D | S | S |
| Architecture, database and API contracts | D | S | R | S | I |
| Frontend integration and UX consistency | S | S | R | S | D |
| Test planning, system testing and evidence | R | S | D | S | R |
| Deployment, configuration and release package | D | S | R | I | I |
| Final report, slides and demonstration | S | S | D | D | S |

## 5. Project Communications

Table 8. Project Communication Plan

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Weekly team planning | All members | Commit weekly scope, owners, dependencies and evidence | Start of each week | Meeting plus Team Tracker |
| Daily coordination | All members | Raise blockers and synchronize active work | Working days, asynchronous | Team chat; short call when needed |
| Weekly supervisor meeting | Team and supervisor | Review progress, decisions, risks and next actions | Before/at each supervisor session | Progress Log, demo and meeting minutes |
| Requirement decision | BA/owner, affected members, supervisor when needed | Confirm ambiguous rules and prevent inconsistent implementation | As needed before development | Decision Log with question, decision, date and evidence |
| Pull request review | Author and reviewer | Verify code, tests, security and API contract | For every merge to protected branch | Git hosting pull request and CI |
| Review/Council readiness | All members | Check product, documentation, testing and demonstration | W4, W8, W12-W15 | Checklist, rehearsal and recorded evidence |
| Incident or blocker escalation | Owner, team lead and affected members | Limit schedule or quality impact | Within one working day | Issue tracker and direct notification |

## 6. Configuration Management

### 6.1 Document Management

Project documents are stored in the shared project workspace with controlled access. Filenames identify the document and version; formal baselines use v1.0, v1.1 and later approved versions. Drafts may use v0.x. Every change records author, date and description. Approved baselines are not overwritten without a recorded change request. Meeting minutes, decisions, feedback and evidence remain linked to the affected deliverable.

### 6.2 Source Code Management

Source code is managed in one HR Connect repository unless the team later approves a justified split. The repository contains frontend, backend and docs areas, and a separate Python AI service (ai-service-v2). Protected main and dev branches require pull requests and CI checks. Feature branches follow a consistent naming rule. Secrets are never committed; .env.example documents required variables. Database changes use versioned migrations and release tags identify reviewed builds.

### 6.3 Tools & Infrastructures

Table 9. Project Tools and Infrastructure

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Frontend: React, TypeScript, Ant Design, Tailwind CSS, Vite. Backend: ASP.NET Core 8 Minimal API with Clean Architecture, MediatR, FluentValidation, EF Core and SignalR. AI service: Python FastAPI with Gemini and Sentence-BERT. |
| Database | PostgreSQL with EF Core versioned migrations and controlled seed data; Cloudflare R2 for private CV and document files. |
| IDEs/Editors | Visual Studio, Visual Studio Code or agreed equivalent. |
| Diagramming | Draw.io, StarUML, Canva or agreed modeling tool; exported diagrams stored with source versions. |
| Documentation | Microsoft Word/Excel/PowerPoint and shared online workspace. |
| Version Control | GitHub repository with protected main and dev branches, pull requests and GitHub Actions CI/CD. |
| Deployment Server | Render (backend), Vercel (frontend), AI service reached through a Cloudflare tunnel; secrets kept in environment variables. |
| Project Management | Official Progress Log plus Team Tracker/issue board for tasks, risks, decisions, feedback and evidence. |
| Testing | xUnit, Moq and FluentAssertions (backend), Vitest and Testing Library (frontend), pytest (AI service), Playwright for end-to-end tests on the deployed system. |
| Communication | Team chat and supervisor meetings; decisions recorded in minutes and the Decision Log. |